## Slide 1
KICK OFF MEETING
วันอังคารที่ 11 กันยายน 2561 งานจ้างเหมาโครงการพัฒนาระบบไฟฟ้าแบบเครือข่ายไฟฟ้า ขนาดเล็กมาก (Micro Grid)
ที่อ าเภอแม่สะเรียง จังหวัดแม่ฮ่องสอน (คพล.)
สัญญาเลขที่ จ. 82/2561
การไฟฟ้าส่วนภูมิภาค

## Slide 2: MEETING AGENDA
Project Detail
Scope of work
Project Management & Project Timeline
Procurement support detail and lead time of delivery
Financial & Accounting support

## Slide 3: Project Detail
Microgrid Maesariang PEA Project Project Information
Project Owner: PEA
Location:
MAESARIANG MAE HONG SON Province Thailand
Scope : EPC
Gunkul Power Development Co., Ltd. NR Electric Co., Ltd (CHINA)

Budget: 132,900,000 THB Incld.VAT
Lead Time Delivery: 360 Days
Sign contract: about: 7 SEP 2018
End of Contract: SEP 2019



## Slide 4: Project Detail
Microgrid Maesariang PEA Project Project Information

## Slide 5: Project Detail
4
Microgrid Maesariang PEA Project Project Information

## Slide 6: Scope Of Work
5
Microgrid Maesariang PEA Project Project Information

## Slide 7: Scope Of Work
6
Microgrid Maesariang PEA Project Project Information

## Slide 8: Project Management & Project Timeline

## Slide 9: Project Management & Project Timeline
(17th Sept18)
(Nov18-Mar19)
(Mar 19- Apr19)
(AUG 19)
7th sept 18
(July19)
3 week
Hand Over
11st Sept 18
(15th Mar 19)
Maesariang Microgrid project : Contract 360 day
1 week
1 week
8 week
17 week
5 week
(Nov18- April19)
(May-June19)
8 week
(17th Nov 18)
1 week
315 Days
12 Sept 18
nd

## Slide 10: Project Management & Project Timeline
9
Microgrid Maesariang PEA Project Organization Chart
Project Director
Mr. Chaiyaporn K.
Asst. Project Director
Mr. Bancha Y. Asst. Project Manager
Mr. Niwat P. Mr. Tinnawat C.
Project Manager
Mr. Krit C.
PEA
Purchasing Support
( )
Engineering Manager
Mr. Jessada P.
Civil Designer
( )
Electrical Designer
( )
NR Electric
Mr. Peter Z.
Construction Manager
Mr. Rawat S.
Civil Work
Mr. Rawat S.
Electrical Work
Mr. Panya K.
Civil Subcontractor
( )
Electrical Subcontractor
( )
NR Electric
(Erection & Comm. Team )

## Slide 11: Procurement Detail Support
Microgrid Maesariang PEA Project
Equipment List

## Slide 12: Procurement Detail Support
Microgrid Maesariang PEA Project
Equipment List

## Slide 13: Procurement Detail Support
12
Microgrid Maesariang PEA Project
Equipment List

## Slide 14
Microgrid Maesariang PEA Project
Financial & Accounting Support

## Slide 15: Financial & Accounting Support
2.Receive Payment 10% (After system study)
10% Payment = 13,290,000THB (Nov 2018)
3.Receive Payment 20% (After FAT)
20% Payment = 26,580,000THB (Apr 2019)
4.Receive Payment 30% (After Installation)
30% Payment = 39,870,000THB (Jun 2019)
5.Receive Payment 20% (After Site Acceptance Test)
20% Payment = 26,580,000THB (July 2019)
6.Receive Last Payment 10% (After system study)
10% Payment = 13,290,000THB (Aug 2019)
Microgrid Maesariang PEA Project
BG Support
  Performance Bond for Advance payment 10% (AUG2018)
  Project warranty bond 10% (SEP2019) 3 years warranty
Payment Term
1.Receive Advance Payment 10%
10% Payment = 13,290,000THB (Sep 2018)

## Slide 16
Gunkul Engineering Public Company Limited
1177 Pearl Bangkok Building, 8th Floor, Phahonyothin Road, Phayathai , Phayathai, Bangkok 10400
15